## Slide 1
Submit potential risk
Project manager evaluation
Is it a risk?
Disregard
NO
YES
Put on RAID sheet
Evaluate risk threat
Is it on the critical path?
Meet with responsible employee(s) and hand-off employee(s) to discuss risk
NO
YES
start
Assign risk to a task(s) or action
What type of risk?
SCOPE
BUDGET
SCHEDULE
Does the risk originate from the client?
NO
YES
Take task(s) out of schedule
Have client submit formal change request
end
Will the risk make cash flow negative?
YES
NO
end
Set up meeting with appropriate team leads
Set up meeting with appropriate team leads
Determine severity of impact on budget
Determine severity of impact to schedule
Update budget appropriately and monitor risk
end
Are reserve funds available?
YES
NO
Pull money from reserves to cover costs
end
What is the risk coming from?
TASKS
SUPPLIES
Can you negotiate an acceptable price?
NO
YES
Get updated price and update project budget accordingly
end
Are there cheaper alternatives?
YES
NO
Order from new supplier and update budget accordingly
end
Discuss matter with appointed supervisor and come up with resolutions
end
Can the task(s) duration be reduced?
YES
NO
Reduce duration of task to save on employee costs
end
Can either predecessors or dependencies be reduced?
YES
NO
Discuss matter with appointed supervisor and come up with resolutions
end
Is there enough slack to compensate?
YES
NO
Monitor task progression to ensure it does not fall behind schedule further
end
Can the task be laddered enough to ensure dependencies do not run late?
YES
Ladder task deliverables so that dependencies start early
end
NO
What is lacking to cause task to run late?
RESOURCES
TIME
Are you able to secure required resources?
YES
NO
Put in order for required resources and deliver when ready
end
Is/are employee(s) willing to work overtime or weekends?
YES
Have employee(s) work overtime/weekends until caught up
end
NO
Are internal employees able to help with workload?
Shift employee(s) around to ensure risk does not become issue
end
NO
Can a subcontractor be hired to expedite work?
NO
YES
YES
Meet with appropriate team lead to explain situation.
end
Hold meeting with team leads explaining impact to schedule and brainstorm ways to solve issue in other project phases
end
Contact appointed supervisor to explain situation
Hire subcontractor and update budget
Update budget
Review change request
Inform affected parties and update plan of record
Approve change(s)
YES
end
NO