## Slide 1: Campus Parking Availability App KLY Inc. By: Mohammad Asif, Dylan Capece, Luke Padgett, Everett McCrea, Blake Stroud

## Slide 2
Summary – Everett McCrea | Current Project Status – Everett McCrea | Financials (internal) – Everett McCrea
KLY Inc. is working on an app that will keep track of the available parking on the UTD campus. This includes showing how many colored parking spots are available at each parking lot by scanning a car’s UTD parking sticker and transmitting that information to a host computer system. Information is aggregated at this host computer system and relayed back to the user via a GUI map that gives a breakdown of available parking at each lot. PM: Everett McCrea | Two testing tasks have ran overtime which is causing a delay in progressing to further testing. As a result, the entire project is running behind the anticipated schedule. Delays in the deployment of the project are expected to occur. | Price to customer: $1,078,745.00 Original budget: $791,665 Original margin: $287,080 Actual cost to date: $480,978 Remaining cost: $310,335 Estimate at completion: $791,665 Current margin: $332
Overview
Current project status: Medium risk (yellow)
Criteria to reach GREEN: Reduce testing time of mobile app and host computer system
Key Achievements – Blake Stroud | Planned Activities – Mohammad Asif | Issues/Risks – Dylan Capece | Major Milestones Achieved – Luke Padgett
Statement of work approved and project official began (Feb. 17) Initial interview with customers concluded (Feb. 29 – Mar. 17) Requirements phase completed (Apr. 1) Design phase officially concluded (May 8) Development phase officially begun (Apr. 9) Testing phase officially begun (Apr. 29) | Finish development of the server/back-end schema (Jun. 18) Finish review/finalization of web page development (May 26) Finish finalization of mobile application testing (Jul. 8) Finish development of service tier applications for the server/back-end system (Jul. 16) Finalize testing of host computer system (Jul. 15) Finalize testing of web page (Jun. 3) Begin setup of the host computer system (Jul. 16) | Issues: Testing of the host computer system’s real time parking lot updates are not complete on time Resolution: Testing Engineer Lead shall work during the next few weekends in order to expedite task and dependencies. Testing of host computer system’s data encryption has ran over expected budget Resolution: Reduce allocated resources for defect testing, regression testing, and end-to-end testing while maintaining current schedule. Risks: Regression testing may not finish on time due to workers being absent. This may cause end-to-end testing to start late. Mitigation: have workers continue work from home office Finalization document of web page testing may not finish on time due to employee conflict. Mitigation: schedule meeting between employees to find compromise on the issue | Current milestones Finalized Requirements document delivered and design phase began (Apr. 1) Finalized Design document delivered and development and testing initialized (May 10) In progress Delivery of finalized development document (Sep. 1) Delivery of finalized testing document (Sep. 24) Delivery of finalized deployment document (Nov. 9)

## Slide 3
Key Milestones Luke Padgett, Blake Stroud
Milestone | Status | % Complete | Planned Start | Actual Start | Planned Finish | Actual Finish | Comments
Finalized Requirements Document | C | 100% | Feb. 19 | Feb. 19 | Apr. 1 | Apr. 3 | Customer interviews delayed by two days due to late completion of interview questions. Meetings conducted online through video sharing program
Finalized Design Document | C | 100% | Apr. 2 | Apr. 4 | May 8 | May 9 | Design began late due to late finishing of requirements phase. Worked quickly to try and keep on schedule.
Finalized Development Document | Y | 78% | Apr. 9 | Apr. 10 | Sep. 1 | N/A | Development began late due to late delivery of design documents.
Finalized Testing Document | Y | 51% | Apr. 29 | Apr. 29 | Sep. 24 | N/A | Able to start on time. Many risks in testing phase threaten to delay project delivery date. Mitigation policies have been put into action.
Finalized Deployment Document | G | 0% | Jul. 16 | N/A | Nov. 9 | N/A | N/A

## Slide 4
 | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Requirements |  |  |  |  |  |  |  |  |  | 
Design |  |  |  |  |  |  |  |  |  | 
Development |  |  |  |  |  |  |  |  |  | 
Testing |  |  |  |  |  |  |  |  |  | 
Deployment |  |  |  |  |  |  |  |  |  | 
Timeline Dylan Capece
Current position

## Slide 5
Key risks Mohammad Asif, Luke Padgett, Blake Stroud, Dylan Capece, Everett McCrea
ITEM | ISSUE/RISK | WORK STREAM | DESCRIPTION | RESOLUTION/MITIGATION | DUE DATE | OWNER
R-1 | Risk | Solution | Development of server/back-end service tier applications may be delivered late and cause delivery of back-end development to delay due to lack of experienced developers | 1) Have development engineer 3 work weekends to catch up to schedule 2) Contract service tier applications workload to 3rd party developer that are experienced with using SQL | 7/16/2020 | Development Engineer 3
R-2 | Risk | Solution | Development of host computer system network between mobile application and RF sensors may be delivered late and cause finalization of host computer system to run late due to a lack of communication between the Design Engineer Lead and Development Engineer Lead | 1) Establish meeting time for design engineer lead and development engineer lead to meet up 2) Have Design Engineer Lead and Development Engineer Lead exchange contact information so that they may contact each other regularly | 4/9/2020 | Design Engineer Lead
R-3 | Risk | Solution | Regression testing may not finish on time, causing end-to-end testing to start late due to test engineer 1 & 2 being absent from work | 1) Have testing engineer lead dedicate extra hour of work each weekday until work is caught up 2) Allow test engineers 1 & 2 to work on regression testing out of office | 7/20/2020 | Testing Engineer Lead
R-5 | Risk | Acceptance | Building of server/back-end schema has not been completed which may result in a delay to the finalization document of the server/back-end development because development engineer 3 was not trained well enough to handle workload | 1) Have Development Engineer Lead help in workload 2) Provide training for Development Engineer 3 to ensure he is adequately prepared for workload 3) Have Design Engineer 2 help with schema development as he has prior experience with it | 7/12/2020 | Development Engineer 3
R-6 | Risk | Solution | Testing of mobile application UI/UX not yet complete, may cause delay in finalizing UI/UX testing due to testing engineer 12 not getting enough work done during work duration | 1) Have testing engineer 12 work extra hours on weekday until caught up 2) Have project manager observe Test Engineer 12's during working hours so that he is pressured to perform better | 7/10/2020 | Testing Engineer 12
Low risk
Medium risk
High risk

## Slide 6
Key Actions Mohammad Asif, Dylan Capece
Project Action List |  |  |  |  |  |  |  |  | 
# | Description | Work Stream | Originator | Owner | Date Assigned | Date Needed | Date Closed | Comments | Status
5 | Diagrams of server/back-end schema shall be sent to UTD database administrator weekly to ensure they are compatible with current UTD database | Acceptance | Development Engineer Lead | UTD Database Administrator | 02-May-20 | 10-Jun-20 | N/A | Ensure that development team is designing the server/back-end schema correctly the first time around to avoid revision | IN PROGRESS
9 | Requirements Team Lead will monitor design team to ensure requirements are captured properly in design blueprints | Acceptance | Requirements Engineer Lead | Design Engineer Lead | 02-Apr-20 | 8-May-20 | 8-May-20 |  | COMPLETED
4 | Development Engineer Lead will provide weekly write-ups to PM regarding development of project | Acceptance | PM | Development Engineer Lead | 09-Apr-20 | Each Friday | N/A | Allow PM to modify schedule based on the input provided in Development Manager Lead's reports | IN PROGRESS
6 | Conduct stakeholder meeting to discuss non-functional requirements at least once a month | Acceptance | PM | PM | 17-Mar-20 | First Tuesday of the month | N/A | Stakeholders should email PM if they will be able to attend | IN PROGRESS

## Slide 7
Decisions Luke Padgett, Everett McCrea
Project Decision List |  |  |  |  | 
# | Description | Owner | Date Decided | Present Parties | Status
D-1 | Development of the mobile application shall be built using Java 8 | Development Engineering Lead | 28-Feb-20 | Development Engineer Lead, Testing Engineer Lead, Design Engineer Lead, PM | COMPLETED
D-3 | Testing environment shall be built using Junit version 4.13 | Testing Engineer Lead | 13-Apr-20 | Testing Engineer Lead, Design Engineer Lead, Development Engineer Lead | COMPLETED
D-4 | The developed database shall be built using SQL version 14.0 | Design Engineer Lead | 21-Feb-20 | Design Engineer Lead, Deployment Engineer Lead, Development Engineer Lead, Testing Engineer Lead, Deployment Engineer Lead, PM | COMPLETED