## Slide 1: Campus Parking Availability App KLY Inc.
Presented by: Mohammad Asif, Dylan Capece, Luke Padgett, Everett McCrea, Blake Stroud
Group 08
Date: September 4, 2020

## Slide 2
Summary – Everett McCrea | Current Project Status – Everett McCrea | Financials (internal) – Everett McCrea
KLY Inc. is working on an app that keeps track of available parking on the UTD campus. This includes showing how many colored parking spots are available at each parking lot by scanning a car’s UTD parking sticker and transmitting that information to a host computer system. Information is aggregated at this host computer system and relayed back to the user via a GUI map that gives a breakdown of available parking at each lot. PM: Everett McCrea | Late task completion in development phase has led to late delivery of development document (milestone 03). Late task completion in testing phases threaten to delay delivery of milestones 04. Project has also faced with risk of not completing deployment tasks on time due to employee leaving company unexpectedly. Currently expediting work by enforcing overtime and actively looking for new candidate to fill role of deployment engineer. | Price to customer: $1,078,745.00 Original budget: $791,665 Original margin: $287,080 Actual cost to date: $639,924.40 Remaining cost: $174,836.20 Estimate at completion: $811,760.60 Current margin: $266,984.40
Overview
Current project status: High risk (red)
Criteria to reach GREEN: Expedite work on remaining development and testing phase tasks.
Key Achievements – Blake Stroud | Planned Activities – Mohammad Asif | Issues/Risks – Dylan Capece | Major Milestones Achieved – Luke Padgett
Review of development document (milestone 03) officially begun (Aug. 26) Testing phase officially begun (Apr. 29) Deployment phase officially begun (Jul. 16) Finished regression testing (Jul. 20) Finished testing of DB schema (Aug. 26) Officially concluded setup of host computer system for client (Jul. 22) | Connection of system components (Sep. 29) Launch of database (Sep. 7) Training camp with client to teach them the system (Oct. 22) Begin drafting testing finalization document (Sep. 21) Finalize testing phase (Sep. 25) Begin defect testing (Sep. 7) Begin capturing car information from parking lot gates (Sep. 28) Begin drafting of final deployment document (Nov. 11) | Issues: Testing of service tier applications may not finish on time due to late delivery of supplies. This has caused the finalization of the server/back-end testing to start past deadline Resolution: Testing Engineer 3 shall work overtime to compensate for late delivery. Risks: Training clients on system may be delayed due to employee leaving company unexpectedly. This may cause the drafting of the deployment document to be delivered late. Mitigation: Borrow Deployment Engineer from another project within KLY Inc. Connection between UTD database and mobile app database may be delayed due to late start of prerequisite task. This may cause the connection of system components to be delayed. Mitigation: Have the Testing Engineer Lead train and help with workload to ensure speedy delivery. | Current milestones Finalized Requirements document delivered and design phase began (Apr. 1) Finalized Design document delivered and development and testing initialized (May 10) In progress Delivery of finalized testing document (Sep. 24) Delivery of finalized deployment document (Nov. 9) Review of development document (Aug. 26)

## Slide 3
Key Milestones Luke Padgett, Blake Stroud
Milestone | Status | % Complete | Planned Start | Actual Start | Planned Finish | Actual Finish | Comments
Finalized Requirements Document | C | 100% | Feb. 19 | Feb. 19 | Apr. 1 | Apr. 3 | Customer interviews delayed by two days due to late completion of interview questions. Meetings conducted online through video sharing program
Finalized Design Document | C | 100% | Apr. 2 | Apr. 4 | May 8 | May 11 | Design began late due to late finishing of requirements phase. Worked quickly to try and keep on schedule.
Finalized Development Document | R | 99% | Apr. 9 | Apr. 10 | Sep. 1 | N/A | Development phase has ran over expected deadline. Shifting all available development engineers into overtime to expedite tasks.
Finalized Testing Document | Y | 91% | Apr. 29 | Apr. 29 | Sep. 25 | N/A | New risks have spawned due to late completion of server/back-end testing. This could cause testing phase to deliver late. Actively assigning more resources to ensure timely delivery.
Finalized Deployment Document | Y | 14% | Jul. 16 | Jul. 16 | Nov. 9 | N/A | Initial tasks completed. Waiting on completion of testing phase before bulk of work can begin. Employee leaving project has created risk – currently searching for suitable replacement.

## Slide 4
 | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Requirements |  |  |  |  |  |  |  |  |  | 
Design |  |  |  |  |  |  |  |  |  | 
Development |  |  |  |  |  |  |  |  |  | 
Testing |  |  |  |  |  |  |  |  |  | 
Deployment |  |  |  |  |  |  |  |  |  | 
Timeline Dylan Capece
Current position (9/4/2020)
Delay due to issues
Customer interviews concluded (3/17/20)
Schema officially built (6/18/20)
Completed schema testing (8/26/20)
Complete setup of host computer system for client (7/22/20)
System go-live and project conclusion (11/20/20)

## Slide 5
Key risks Mohammad Asif, Luke Padgett, Blake Stroud, Dylan Capece, Everett McCrea
ITEM | ISSUE/RISK | WORK STREAM | DESCRIPTION | RESOLUTION/MITIGATION | DUE DATE | OWNER
R-12 | Risk | Launch of database may be late due to testing engineer 3 having not started prerequisite task of finalizing server/back-end testing on time. This may delay the connection of systems components. | 1) Have Testing Engineer 3 work overtime to complete prerequisite task so that the launch of database can occur on schedule 2) Assign Testing Engineer Lead to help with the finalization of server/back-end testing | 1) Have Deployment engineer 3 work overtime to launch database as soon as possible 2) Have Deployment Engineer 1 work with Deployment Engineer 3 to expedite work | 9/9/2020 | Testing Engineer 3
R-11 | Risk | Defect testing may finish late due to test engineer 3 not starting prerequisite task of finalizing server/back-end testing on time. This may cause the drafting of the final testing document to run late. | 1) Have Testing Engineers 1 & 4 help with finalizing the server/back-end document 2) Assign additional employees to defect testing (testing engineers 5, 10, and 11) to expedite the work and shorten the schedule | 1) Assign Testing Engineer Lead to both the prerequisite task (finalizing server/back-end testing) and defect testing to help with workload 2) Have Testing Engineer 1, 4, 6, 8, and 9 work overtime on defect testing to ensure it completes on time | 9/18/2020 | Testing Engineer 3
R-15 | Risk | Capturing of car information from parking lot gates may be late due to Deployment Engineer 4 unexpectedly terminating employment. This may cause the connection of system components to run late due to lack of employee resources. | 1) Begin searching for permanent replacement employee to take on responsibilities of Deployment Engineer 4 2) Give workload to Deployment Engineer 1 3) Contract temporary worker to fill in for Deployment Engineer 4 | 1) Request for additional employee working on another project within the company 2) Have Deployment Engineer 1 work weekends and overtime to catch up on the work left behind by Deployment Engineer 4 | 9/28/2020 | PM
R-16 | Risk | Connection of system components may be delivered late due to Deployment Engineer 4 unexpectedly terminating employment. This may cause a delay in training the clients on the system. | 1) Begin searching for replacement employee 2) Give workload to Deployment Engineer 2 3) Have Deployment Engineer Lead work weekends on his tasks as well as tasks left behind by Deployment Engineer 4 | 1) Begin connection of system components immediately with subcomponents that have already been delivered so that work can begin earlier than expected 2) Request for additional employee working on another project within the company | 10/20/2020 | PM
R-20 | Risk | Release of the mobile application on to the Apple App Store may be late due to unexpectedly long waiting time for a response back from Apple representative. This may cause the training of the clients to start and end late. | 1) Have Deployment Engineer 3 call Apple weekly to get a response 2) Set up video meeting between Deployment Engineer 3, PM, and an Apple representative to move along the process of publishing project's mobile application to the Apple App Store | 1) Have internal upper management attempt to get a hold of Apple representative using their connections at the company 2) Send formal letter to Apple with request of publishing an App on their Apple App Store | 10/21/2020 | Deployment Engineer 3
Low risk
Medium risk
High risk

## Slide 6
Key Actions Mohammad Asif, Dylan Capece
Project Action List
# | Description | Work Stream | Originator | Owner | Date Assigned | Date Needed | Date Closed | Comments | Status
6 | Conduct stakeholder meeting to discuss non-functional requirements at least once a month | Acceptance | PM | PM | 17-Mar-20 | First Tuesday of the month | N/A | Stakeholders should email PM if they will be able to attend | IN PROGRESS
9 | Requirements Team Lead will monitor design team to ensure requirements are captured properly in design blueprints | Acceptance | Requirements Engineer Lead | Design Engineer Lead | 02-Apr-20 | 8-May-20 | 8-May-20 |  | COMPLETED
4 | Development Engineer Lead will provide weekly write-ups to PM regarding development of project | Acceptance | PM | Development Engineer Lead | 09-Apr-20 | Each Friday | N/A | Allow PM to modify schedule based on the input provided in Development Manager Lead's reports | IN PROGRESS
5 | Diagrams of server/back-end schema shall be sent to UTD database administrator weekly to ensure they are compatible with current UTD database | Acceptance | Development Engineer Lead | UTD Database Administrator | 02-May-20 | 10-Jun-20 | 12-Jun-20 | Ensure that development team is designing the server/back-end schema correctly the first time around to avoid revision | COMPLETED
7 | Design Engineer Lead and Deployment Engineer Lead shall meet once a month to review how connection of system should work at deployment time | Acceptance | Design Engineer Lead | Deployment Engineer Lead | 20-Jun-20 | 19-Nov-20 | N/A | Meetings shall take place on the first Tuesday of each month at 7:00 PM and Design Engineer shall walkthrough how the various systems interconnect with each other | IN PROGRESS
14 | Deployment Engineer Lead shall keep UTD database administrator up-to-date about the launch of the database when it is time for database to be deployed | Acceptance | Deployment Engineer Lead | UTD Database Administrator | 2-Sep-20 | 9-Sep-20 | N/A | Deployment Engineer Lead will let UTD database administrator know any complications in the launch of the database and shall let him/her know when the database is ready to be turned on | IN PROGRESS

## Slide 7
Decisions Luke Padgett, Everett McCrea
Project Decision List
# | Description | Owner | Date Decided | Present Parties | Status
D-1 | Host computer system will use the Ubuntu OS version 19.10 | Development Engineer Lead | 20-Feb-20 | Development Engineer Lead | CLOSED
D-2 | UTD's database administrator will need to be present during the customer interviews to provide information regarding the design of the UTD schema | Requirements Engineering Lead | 20-Feb-20 | Requirements Engineering Lead, UTD database administrator | CLOSED
D-3 | The developed database shall be built using SQL version 14.0 | Design Engineer Lead | 21-Feb-20 | Project Manager, Design Engineer Lead, Requirements Engineer Lead, Development Engineer Lead, Testing Engineer Lead | CLOSED
D-4 | Development of the mobile application shall be built using Java 8 | Development Engineering Lead | 28-Feb-20 | Requirements Engineer Lead, Development Engineer Lead, Testing Engineer Lead, Design Engineer Lead | CLOSED
D-5 | Meetings between customer and team members shall take place via Skype instead of face-to-face | PM | 1-Apr-20 | UTD Upper management, PM | OPEN
D-6 | Testing environment shall be built using Junit version 4.13 | Testing Engineer Lead | 13-Apr-20 | Test Engineer Lead, Test Engineers 1 - 12 | CLOSED
D-7 | UTD database administrator and UTD network administrator shall be present when deployment team is connecting system together. | UTD database administrator | 1-Sep-20 | Deployment Engineer Lead, UTD database administrator, UTD network administrator | OPEN
D-8 | Testing Engineer 12 will act as a stand-in for the Testing Engineer Lead during the Drafting, Review, and Finalization of the testing phase document. | Testing Engineer 3 | 3-Sep-20 | PM, Testing Engineer 12, Testing Engineer Lead | OPEN