## Risks
High Risk
Med Risk | Project - Issues and Risks | [6 empty] | DashBoard?
Low Risk | Item # | Issue/Risk | Description | Resolution Plan / Mitigation Plan | Contingency Plan | Due Date | Owner
| R-1 | Risk | Design of host computer system components may be late 4 days | Have design engineer 1 work overtime/weekends | Borrow additional design engineers from other projects within the company | 2020-04-30 | Designer 1 | N
| R-2 | Risk | Design of server/back-end components may be late 3 days | Have design engineer 2 work overtime/weekends | Borrow additional design engineers from other projects within the company | 2020-04-30 | Designer 2 | N
| R-3 | Risk | Design of mobile application may be late by 3 days | Have design engineer 3 work overtime/weekends | Borrow additional design engineers from other projects within the company | 2020-04-30 | Designer 3, Design Engineer Lead | N
| R-4 | Risk | Final design document may be late by 3 days | Conduct meeting between Project Manager, Design Engineering Lead, Development Engineering Lead, and Testing Engineering Lead on following weekend | Have design engineer lead finalize document without other parties involved | 2020-05-08 | Design Engineer Lead | N
| R-5 | Risk | Final development document may be delivered late by 3 days | Development Engineer Lead and PM work following weekend to complete Line item 118 (review development document) so they can start finalization on time | Have development engineer lead finalize document without other parties involved | 2020-09-01 | Development Lead | N
| R-6 | Risk | Development of server/back-end may be late by 3 days | Have development engineer 3 work overtime/weekends | Borrow additional development engineers from other projects within the company | 2020-08-13 | Development Engineer 3 | N
| R-7 | Risk | Testing of server/back-end may be late by 3 days | Have testing engineer 3 work overtime/weekends | Borrow additional testing engineers from other projects within the company | 2020-09-10 | Testing Engineer 3 | N
| R-8 | Risk | Launch of database may be late by 3 days | Have deployment engineer 3 work weekend inbetween start and end data | Work on other items from following dependency (connect system components) and come back to connect database once its completed | 2020-09-15 | Deployment Engineer 3 | N
| R-9 | Risk | Defect testing may start late by 2 days | Have testing engineers 1, 4, 6, 8, and 9 work overtime/weekends | Borrow additional testing engineers from other projects within the company | 2020-09-29 | Testing Engineer 1, Testing Engineer 4, Testing Engineer 6, Testing Engineer 8, Testing Engineer 9 | N
| R-10 | Risk | Connection of system may be late by 2 days | Have development engineer lead and deployment engineer lead connect system components as they leave development | Reduce number of days UTD employees get to train so project still makes deadline | 2020-11-06 | Deployment Engineer 4, Deployment Engineer Lead, Development Engineer Lead | N

## Issues
High Risk
Med Risk | Project - Issues
Low Risk | Item # | Issue/Risk | Description | Resolution Plann / Mitigation Plan | Due Date | Owner
| I-01 | Issue | Requirements team did not finish interview questions on time and are now late to interview with customer | Schedule interview with customer at their earliest next available time and reduce number of interview days from 14 to 10 | 2020-03-11 | Requirements Engineering Lead, PM
| I-02 | Issue | Finalized project requirements is not ready to deliever to design team by deadline due to customer interviews being held late | Have requirements engineer lead work overtime to ensure document is ready at the earliest date possible | 2020-04-06 | Requirements Engineering Lead, PM

## Actions
Project Action List
# | Description | Originator | Owner | Date Assigned | Date Needed | Date Closed | Comments | Status
1 | Start development of system's functional components as soon as their design documents are finalized | Development Engineer Lead | Development Engineer Lead | 2020-04-03 | 2020-09-01 |  |  | IN PROGRESS
2 | Start testing of system's components as soon as their development is finalized | PM | Testing Engineer Lead | 2020-04-09 | 2020-10-14 |  |  | IN PROGRESS
3 | Launch the database as soon it testing is finished | PM | Deployment Engineer Lead | 2020-09-09 | 2020-09-10 |  |  | OPEN
4 | Release mobile application to app stores as soon as system is connected and operational | Deployment Engineer Lead | Deployment Engineer Lead | 2020-10-16 | 2020-11-09 |  | Stores not including Apple App Store and Google Play store are not required | OPEN
5 | Have appropriate team lead participate in the review and finalization of deliverable documents | PM | Requirements Engineering Lead, Design Engineering Lead, Development Engineering Lead, Testing Engineering Lead, Deployment Engineering Lead, PM | 2020-02-21 |  |  |  | OPEN
6 | Have project manager review and finalize all deliverable documents | Requirements Engineer Lead | PM | 2020-02-21 |  |  | Have PM assure that deliverable document is correctly formatted | IN PROGRESS
7 | Have testing lead conduct end-to-end testing | Testing Engineer Lead | Testing Engineer Lead | 2020-08-24 | 2020-10-07 |  | Testing Engineer Lead familiar with end-to-end testing practices | OPEN
8 | Interview customer regarding non-functional requirements | PM, Requirements Engineer Lead | Requirements Engineer Lead | 2020-02-27 | 2020-03-17 | 2020-03-17 | Conduct during scheduled time on the schedule | CLOSED
9 | Schedule additional interview with customer to confirm requirements of the system | PM | PM, Requirements Engineering Lead | 2020-03-03 | 2020-03-17 | 2020-03-17 | Interview should be after first-round interviews have all completed | CLOSED
10 | Contact development engineer lead each week to check in on progress | PM | Development Engineer Lead, PM | 2020-04-09 |  |  | Check-ins will be held each Thursday at 4:00 pm | IN PROGRESS

## Decisions
Project Decision List
# | Description | Owner | Date | Comments | Status
D-1 | Requirements interviews will be conducted with all able-bodied requirement engineers present | PM | 2020-02-28 | Requirements Engineer 2 is not able to make it to the client interviews due to unforseen accident | CLOSED
D-2 | Decide on which technology (backend languages, frontend languages, OS, mobile application languages, and network connections) the project should implement will be made by the appropriate lead (development lead, design lead, etc.) | PM | 2020-02-20 | Development lead will make final decision for which supplies the development team will use | OPEN
D-3 | Client reviews will be held monthly to go over overall project development | Requirements Lead | 2020-02-19 | Ensure client is on board with how the project is developing | OPEN
D-4 | All team leads will participate in the finalization of the requirements document | PM | 2020-04-01 | Ensure that each team lead understands what the requirements need to be developed throughout the project | OPEN
D-5 | Each requirements engineer shall draft interview questions for a different functional area of the project | Requirements Lead | 2020-02-19 | Put the requirements engineers on functional area they are most comfortable to speed up progress | CLOSED