## Sheet1
Flow step | Details
Submit potential risks | Employee or PM must submit potential risk for PM's consideration
Project manager evaluation | PM reviews risk
Is it a risk? | PM determines if the potential risk is an actual risk
Disregard | If the potential risk does not turn out to be a risk, disregard the concern
Put on RAID sheet | If potential risk is real, write it down on the RAID sheet
Evaluate risk threat | Evaluate which level of risk (low, medium, high) the risk falls under
Assign risk to a task(s) or action | Assign the risk to a specific item of work in the WBS or MPP schedule
What type of risk? | Determine if the risk deals with the scope, budget, or schedule of the project
Does the risk originate from the client? | If the risk deals with the scope, determine if this change in scope came from client
Take task(s) out of schedule | If the scope risk did not come from the employee, then it is not in the SoW, therefore do not continue working on it
Have client submit formal change request | If the scope risk came from the client, have them submit a change request so the project can be renegoiated
Review change request | Look over how this change would affect the project and whether or not you need to ask the client for more funds/time.
Approve change(s)? | Is the change worth implementing into the project?
Inform affected parties and update plan of record | make sure those in charge of working on the new tasks are informed of what they have to do
Set up meeting with appropriate team leads | If a risk is posed to either the buget or schedule, set up a meeting with the team lead in which phase the risk may impact
Determine severity of impact to schedule | With the team lead, come up with a way of quantifying the risk severity
Is it on the critical path? | If the risk impacts the schedule, determine if the risk imapcts the critical path
Meet with responsible employee(s) and hand-off employee(s) to discuss risk | If on the critical path, meet with the employees working on the task
Is there enough slack to compensate? | If the task is not on critical path, determine if the provided slack is enough
Monitor task progression to ensure it does not fall behind schedule further | If enough slack is provided, keep an eye on risk to make sure it does not become an issue
Can the task be laddered enough to ensure dependencies do not run late? | If the task is on critical path, can the tasks be laddered so dependencies are not impacted as much
Ladder task deliverables so that dependencies start early | If it can be laddered, ladder the activity.
What is lacking to cause task to run late? | Determine what is causing the task to run late (supplies or time)
Are you able to secure required resources? | Determine if resource acquisition is possible to help expedite the task at hand
Put in order for required resources and deliver when ready | If the PM can get resources to remove risk, do so
Is/are employee(s) willing to work overtime or weekends? | If risk is associated with time, determine if employees will work more (overtime) to compensate
Have employee(s) work overtime/weekends until caught up | If employees are willing to work more (overtime), have them work extra hours
Are internal employees able to help with workload? | If employees are not willing to work extra, determine if there are more employees on the project that are able to help
Reorganize employees to ensure risk does not become issue | If there are employees on the project able to help, send them to work on the risk task
Can a subcontractor be hired to expedite work? | If there are no employees able to help work on risk task, determine if hiring a subcontractor will correct the risk
Meet with appropriate team lead to explain situation. | If a subcontractor can be hired, first meet with team leads to explain situation
Hire subcontractor and update budget | Hire a subcontractor and report budget changes
Hold meeting with team leads explaining impact to schedule and brainstorm ways to solve issue in other project phases | If you cannot hire a subcontractor, meet with all the project phase team leads to come up with a solution
Contact appointed supervisor to explain situation | PM should contact their boss to report the situation
Set up meeting with appropriate team leads | If the risk is associated with the budget, meet up with appropriate team lead impacted by risk
Determine severity of impact on budget | Determine the risk's impact on the project budget
Will the risk make cash flow negative? | Determine if the risk makes the cash flow of the project run into the negatives
Update budget appropriately and monitor risk | If the risk does not make cash flow negative, update the budget according to risk cost and monitor it so it does not get too severe
Are reserve funds available? | If the cash flow becomes negative, are there reserved funds you can use to combat the risk?
Pull money from reserves to cover costs | If reserve funds are available, pull money from reserve to deal with risk
Update budget | Update the budget to reflect the risk's impact
What is the risk coming from? | If there are no reserve funds, determine if risk is coming from supplies or tasks
Can you negotiate an acceptable price? | If risk is coming from supplies, is it possible to get a bargain
Get updated price and update project budget accordingly | If you can get a bargain, take deal and update budget
Are there cheaper alternatives? | If a bargain cannot be negotiated, are the other supplies that are cheaper to purchase
Order from new supplier and update budget accordingly | If cheaper supplies exist, buy those instead and update budget
Discuss matter with appointed supervisor and come up with resolutions | If no cheaper supplies exist, discuss the matter with PM's supervisor
Can the duration of the task(s) be reduced? | If risk is coming from tasks, determine if overall duration of task can be reduced
Reduce duration of task to save on employee costs | If the duration of the task can be reduced, reduce it as to save money on employee costs
Can either predecessors or dependencies be reduced? | If the task cannot be reduced, can either its dependent tasks or preceeding tasks be reduced
Discuss matter with appointed supervisor and come up with resolutions | If neither preceding or dependent tasks can be reduced, discuss matter with PM's supervisor