## Governance Plan
Luke Padgett, Blake Stroud
Meeting / Governance Model
Meeting | Meeting Day | Meeting Time | Input | Structure | Output | Owner | Participants
Requirements Team Technica Meeting | Monday | 8:00 - 9:30 AM | Technical topics regarding the requirements collection, analysis, or implementation of the project | List of topics are gathered by Requirements Engineer Lead based off risks, issues, questions, and reviews of last week's work. Agenda is passed out at start of meeting. | Technical decisions to resolve risks and issues facing requirements phase. | Requirements Engineer Lead | Requirements Engineer 1, 2, 3, 4, 5 Requirements Engineer Lead Optional Attendees: Project Manager
Design Team Technical Meeting | Monday | 9:30 - 11:00 AM | Technical topics regarding the design of the project's systems and how to incorporate gathered requirements into design blueprints. | List of topics are gathered by Design Engineer Lead based off risks, issues, questions, and reviews of last week's work. Agenda is passed out at start of meeting. | Technical decisions to resolve risks and issues facing design phase. | Design Engineer Lead | Design Engineer 1, 2, 3, 4, 5 Design Engineer Lead Optional Attendees: Project Manager
Development Team Technical Meeting | Monday | 11:00 AM - 12:30 PM | Technical topics regarding the development/coding of the system. | List of topics for discussion include analysis of unit testing results, defect testing, and regression testing. Testing Engineer Lead is to forward topics to Development Engineer Lead day before meeting. Agenda shall be passed out during meeting. | Technical descisions on how to resolve defects found during testing. | Development Engineer Lead | Development Engineer 1, 2, 3, 4, 5, 6, 7, 8, 9 Development Engineer Lead Optional Attendees: Project Manager
Testing Team Technical Meeting | Tuesday | 10:00 - 12:00 PM | Technical topics regarding the testing of the developed codebase. | List of topics for discussion will be based off the developed code provided by the Development Engineer Lead. Development Engineer Lead should forward developed code changes to Testing Engineer Lead day before meeting. Agenda shall be passed out during meeting. | Technical decisions on how to test provided code and how to measure adherence to functional/non-functional requirements | Testing Engineer Lead | Testing Engineer 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12 Testing Engineer Lead Optional Attendees: Project Manager
Deployment Team Technical Meeting | Friday | 2:00 - 3:00 PM | Technical topics regarding the deployment of the system to the customer and integration of all sub-systems. | Discussion shall be limited to integration of systems provided by development team. Agenda shall be passed out passed out before meeting begins. | Technical decisions on how to integrate system subcomponents together. | Deployment Engineer Lead | Deployment Engineer 1, 2, 3, 4 Deployment Engineer Lead Optional Attendees: Project Manager
Project Status and Overview Meeting (internal) | Wednesday (bi-weekly) | 3:00 - 5:00 PM | Project dashboard | Review project dashboard, explain key risks and issues, explain mitigation strategies and contingencies plans, provide estimations for budget and schedule. | Decisions on how to reduce budget and schedule of project | Project Manager | Project Manager, Development Engineer Lead, Requirements Engineer Lead, Testingn Engineer Lead, Internal upper management, Deployment Engineer Lead, Design Engineer Lead Optional Attendees: Testing Engineer 12
Project Development Meeting (external) | TBD | After 4:00 PM | Project dashboard | Review project dashboard and discuss key technical accomplishments. Provide schedule estimate. | Meeting minutes, milestone delivery sign off | Project Manager UTD upper management | Project Manager, UTD upper management, Internal upper management Optional Attendees: Development Engineer Lead
Project Technical Meeting (external) | Tuesday | 8:00 - 10:15 AM | Technical topics regarding the infrastructure of UTD systems and networks | Discuss how project should be developed to ensure integration into UTD's software infrastructure. Agenda shall be emailed day before meeting. | Technical answers on how development and design team should proceed to ensure project integrates into UTD infrastructure | Development Engineer Lead, UTD database administrator, UTD network administrator | Design Engineer Lead, Development Engineer Lead, Testing Engineer Lead, Deployment Engineer Lead, UTD Database administrator, UTD network administrator, UTD IT department Optional Attendees: Project Manager
Team Lead Non-technical Meeting (internal) | Thursday | 3:00 - 4:45 PM | Non-technical topics that need to be resolved. | Review any conflicts or planned absences regarding the project team. | Conflict reports, absence requests | Project Manager | Requirements Engineer Lead, Design Engineer Lead, Development Engineer Lead, Testing Engineer Lead, Deployment Engineer Lead, Project Manager Optional Attendees: internal upper management