## Risks
High Risk |  |  |  |  | Dylan Capece, Blake Stroud, Luke Padgett, Everett McCrea, Mohammad Asif
Med Risk | Project - Issues and Risks | [6 empty] | DashBoard?
Low Risk | Item # | Issue/Risk | Description | Resolution Plan / Mitigation Plan | Contingency Plan | Due Date | Owner
| R-1 | Risk | Finalized web interface requirements questions not delivered on time, may cause delay in finalization of project requirements document due to requirements engineer 3 being absent from work | 1) Have requirements engineer 3 work weekends to catch up to schedule 2) Allow requirements engineer 3 to work from home during absence | 1) Dedicate all available requirements team employees to catch up task on time 2) Contract work to another team within the company | 2020-04-09 | Requirements Engineer 3 | Y
| R-2 | Risk | Finalized UI/UX requirements questions not yet completed due to requirements engineer 5 being absent from work. This may cause the finalized requirements doucment (milestone 01) to be delivered late. | 1) Have requirements engineer 5 come in on weekends until work is caught up 2) Allow requirements engineer 5 to work from home during absence 3) Assign workload to requirements engineer 4 who has prior experience with drafting UI/UX requirements questions | 1) Put requirements engineer 1 and 2 on same task to expedite delivery 2) Hire new requirements engineer to do workload | 2020-04-10 | Requirements Engineer 5 | Y
| R-3 | Risk | Design of network connections (App & hardware) may not finish on time due to delays in delivering final project requirements document. This may delay the review of the host computer system design | 1) Have design engineer 1 work additional hour each weekday to ensure task is delivered on time. | 1) Have design engineer lead share workload to ensure document is delivered as soon as possible. | 2020-04-17 | Design Engineer 1 | Y
| R-4 | Risk | Design of server/back-end schema may not finish on time due to delays in delivering final project requirements document. This may delay the review of the server/back-end design | 1) Design engineer 2 should stop work on simultaneous tasks to focus solely on completing this task 2) Contract 3rd party back-end designers to help with schema design | 1) Have design engineer lead share workload to ensure document is delivered as soon as possible. 2) Pull in external company resources to expedite delivery of task | 2020-04-21 | Design Engineer 2 | N
| R-5 | Risk | Design of mobile application's UTD map display may finish late due to delays in delivering final project requirements document. This may delay the review of the mobile application design | 1) Have design engineer 2 help with workload to ensure task delivered on time 2) Start design of mobile application map display early as soon as customer provides requirements for its design instead of waiting for finalization of requirements document | 1) Have design engineer 2 and 3 come in on weekends to finish task 2) have design engineer 3 drop all other tasks and focus solely on delivery of the mobile application UTD map display design | 2020-04-13 | Design Engineer 3 | Y
| R-6 | Risk | Design of web page payment page may not finish on time due to delays in delivering final project requirements document. This may delay the review of the web page design | 1) Have design engineer 4 work overtime of 3 hours each day to ensure timely delivery 2) Look foor pre-made paymenet page UI/UX templates available online to use | 1) Have design engineer 4 come in on weekends to work in addition to working overtime 2) Contract design of web page payment page to 3rd party company | 2020-04-09 | Design Engineer 4 | Y
| R-7 | Risk | Design of web page UI/UX may not finish on time due to delays in delivering final project requirements document. This may cause the review of the UI/UX to be delivered late | 1) Have design engineer 5 work overtime of 1 hour each day to ensure timely delivery 2) Assign development engineer 7 to help with workload as she has experience with UI design | 1) Have design engineer 4 come in on weekends to work on task 2) hire additional design engineer to help in workload | 2020-04-09 | Design Engineer 5 | N
| R-8 | Risk | Design of CRUD applications may be delivered late due to prolonged absence of design engineer 2. This may delay the review of the server/back-end design. | 1) Split task workload with design Engineer 1 2) Contract 3rd party back-end designers to help with workload 3) Allow design engineer 2 to work on tasks while absent from the office | 1) Have design engineers 1, 3, and 5 come in over the weekends to finish task 2) Use design of CRUD applications from similar previous as a baseline and make slight changes so that they fit with current project | 2020-04-10 | Design Engineer Lead | N
| R-9 | Risk | Persistent conflict between Design Engineer 1 and Design Engineer Lead may cause the review of the host computer design to be late. This may delay the delivery date of the finalized host computer design | 1) Schedule conflict meeting with design engineer 1 and design engineer lead to come to a compromise on the issue. | 1) Give authority of which data encryption design to use for the project to design engineer lead and have design engineer 1 and design engineer lead work weekends to catch up on task | 2020-04-28 | Project Manager | N
| R-10 | Risk | Extended poor performance from design engineer 5 may delay the finish time of the design web page UI/UX task. This may delay the review of the UI/UX design | 1) Bring in design engineer 5 for a performance review and solve issues that are preventing him from performing normally 2) Watch over design engineer 5 during work hours to ensure he is pressured to complete work | 1) Pull in more resources from company to take over workload of design engineer 5 2) Contract 3rd party back-end developer to design the web page UI/UX | 2020-04-11 | Project Manager | N

## Issues
High Risk
Med Risk | Project - Issues
Low Risk | Item # | Issue/Risk | Description | Impact | Resolution Plann / Mitigation Plan | Due Date | Owner
| I-01 | Issue | Customer interviews not conducted on time due to requirements questions being incomplete. Interviews will be rescheduled to later date which will delay drafting of final requirement document | Drafting of final requirements document will be delayed until customer interviews can be conducted | Perform video meetings so that physical attendance is not required and meeting can be conducted earlier. | 2020-04-09 | Requirements Engineer Lead
| I-02 | Issue | Finalized requirements document (milestone 01) not delivered on time due to absence of requirements engineer team memebrs. This is causing design phase to start late | Design phase will begin late | Have all requirements engineers and the requirements engineer lead work on task delivery and dedicate extra 2 hours of work towards accomplishing task each day | 2020-04-12 | Requirements Engineer Lead

## Actions
Project Action List
# | Description | Originator | Owner | Date Assigned | Date Needed | Date Closed | Comments | Status
1 | Design Engineers 1 - 5 will monitor development team to ensure their implementation is correct with design blueprints | Design Engineer Lead | Development Engineer Lead | 2020-04-12 | 2020-05-08 |  | Design engineers should only check in with development engineers once a day | IN PROGRESS
2 | Testing Engineer Lead will meet with Development Team Lead reguarly to discuss issues regarding development process | Testing Engineer Lead | Development Engineer Lead | 2020-04-29 | 2020-09-24 |  |  | IN PROGRESS
3 | Requirements Engineer Lead will hold meeting with development department on a bi-weekly basis to clear up requirements development | Requirements Engineer Lead | Development Engineer Lead | 2020-04-09 |  |  | Ensure that requirements are being properly implemented during development | IN PROGRESS
4 | Development Engineer Lead will provide weekly write-ups to PM regarding development of project | PM | Development Engineer Lead | 2020-04-09 |  |  | Allow PM to modify schedule based on the input provided in Development Manager Lead's reports | IN PROGRESS
5 | Testing Engineer Lead and Deployment Engineer Lead shall meet up twice a month to discuss to discuss hand-off items | Testing Engineer Lead | Deployment Engineer Lead | 2020-05-02 |  |  | Determine what items can be given to deployment team early so that not everything is dumped on them at once | IN PROGRESS
6 | Conduct stakeholder meeting to discuss non-functional requirements at least once a month | PM | PM | 2020-03-17 |  |  | Stakeholders should email PM if they will be able to attend | IN PROGRESS
7 | Design Engineer Lead and Deployment Engineer Lead shall meet once a month to review how connection of system should work at deployment time | Design Engineer Lead | Deployment Engineer Lead | 2020-06-20 | 2020-11-09 |  |  | IN PROGRESS
8 | Requirements team will hold daily meetings in the morning to discuss progression of interview questions | Requirements Engineer Lead | Requirements Engineer Lead | 2020-02-19 |  | 2020-02-27 |  | CLOSED
9 | Requirements Team Lead will monitor design team to ensure requirements are captured properly in design blueprints | Requirements Engineer Lead | Design Engineer Lead | 2020-04-02 |  | 2020-05-08 |  | CLOSED
10 | Contact development engineer lead each week to check in on progress | PM | PM | 2020-04-09 |  |  | Check-ins will be held each Thursday at 4:00 pm | IN PROGRESS

## Decisions
Project Decision List
# | Description | Owner | Date | Comments | Status
D-1 | Development of the mobile application shall be built using Java 8 | Development Engineering Lead | 2020-02-28 | Java 8 is the language most capable for accomplishing building the mobile application and will allow the development team to utilize preexisting frameworks to help in the development of the mobile application Attendees: Requirements Engineer Lead, Development Engineer Lead, Testing Engineer Lead, Design Engineer Lead | CLOSED
D-2 | Host computer system will use the Ubuntu OS verion 19.10 | Development Engineer Lead | 2020-02-20 | OS was chosen for its secure architecture and lack of preinstalled software packages. Attendees: Development Engineer Lead | OPEN
D-3 | Testing environment shall be built using Junit version 4.13 | Testing Engineer Lead | 2020-04-13 | Most test engineers know how to use Junit from previous work experience. Attendees: Test Engineer Lead, Test Engineers 1 - 12 | OPEN
D-4 | The developed database shall be built using SQL version 14.0 | Design Engineer Lead | 2020-02-21 | Most employees working on the project know SQL better than any other relation database language, allowing us to save time on development of the server/back-end Attendees: Project Manager, Design Engineer Lead, Requirements Engineer Lead, Development Engineer Lead, Testing Engineer Lead
D-5 | UTD's database administrator will need to be present during the customer interviews to provide information regarding the design of the UTD schema | Requirements Engineering Lead | 2020-02-20 | Understanding the schema design of UTD's database is very important to know during early phase of project so that the mobile application services are not design incorrectly Attendees: Requirements Engineering Lead, customer