## Slide 1
Submit potential risk
Project manager evaluation
start
Will it affect scope, budget, or schedule if it occurs?
NO
YES
Not a risk
Set up meeting with person(s) who submitted risk
Tentatively place risk in RAID sheet
Associate risk with specific project task
Does task have schedule slack to compensate for risk delaying delivery?
NO
What is the probability of the risk occurring?
LOW
(<15%)
MEDIUM
(15%< x <40%)
HIGH
(>40%)
Set up meeting with team where risk originates from to brainstorm mitigations/ contingencies
Update RAID sheet with severity, mitigation, and contingency
Have employee(s) working on task come in on weekends to finish task on time
Monitor risk daily and receive updates from team where risk originated
Set up meeting with team where risk originates from to brainstorm mitigations/ contingencies
Update RAID sheet with severity, mitigation, and contingency
Have employee(s) working on task to work extra 2 hours each weekday to ensure task finishes on time
Project manager should brainstorm mitigations/ contingencies for risk
Update RAID sheet with severity, mitigation, and contingency
Monitor risk bi-weekly by getting updates from the team lead responsible for the at-risk task(s)
YES
Would the risk make the task go over its predicted budget?
NO
YES
Does the risk change the project/task scope?
NO
YES
Continue to monitor and mitigate risks until they are resolved
Set up meeting with team lead who leads the project phase in which the risk was detected
Does the risk make the project go cash flow negative?
NO
YES
Update RAID sheet – add severity, mitigation, and contingency
Cut back all superfluous resources working on task
Monitor risk weekly by getting updates from the team lead responsible for the at-risk task(s)
Have employee(s) working on task to work 2 extra hours each week to ensure task finishes on time
What percentage does the task go over budget?
LOW <25%
MEDIUM 25%< x 45%
HIGH >45%
Monitor risk daily and receive updates from team where risk originated weekly
Update RAID sheet – add severity, mitigation, and contingency
Update RAID sheet – add severity, mitigation, and contingency
Update RAID sheet – add severity, mitigation, and contingency
Cut back resources working on task by 65%
Monitor risk daily and receive updates from team where risk originated weekly
Cut back resources working on task by 10%
Monitor risk monthly and receive updates from team where risk originated monthly
Cut back resources working on task by 30%
Monitor risk weekly and receive updates from team where risk originated bi-weekly
Hold meeting with Requirements Engineer team lead
How much work does this risk add to the task?
LOW >10%
MEDIUM
10% < x < 25%
HIGH >25%
Update RAID sheet – add severity, mitigation, and contingency
Update RAID sheet – add severity, mitigation, and contingency
Update RAID sheet – add severity, mitigation, and contingency
Allocate additional 25% of necessary resources to task
Edit PMP to account for change in scope
Have working team email PM updates weekly to monitor the development of the risk
Edit PMP to account for change in scope
Edit PMP to account for change in scope
Have working team come in on weekends to make up for additional work
Have working team email PM updates bi-weekly to monitor development of risk
Have working team spend 2 hours overtime on weekdays to account for additional work
Have working team email PM updates monthly to monitor development of risk