## Sheet1
Flow Step | Flow Step
Submit potential risk | A risk is generated from a team member or project manager. Risk is forwarded to the project manager for further evaluation
Project manager evaulation | Project manager will look over the submitted risk and evaluate it to determine if the risk poses a threat to changing either the scope, budget, or schedule of the project overall
Will it affect scope, budget, or schedule if it occurs? | Project manager must determine if the submitted risk has the chance of changing the scope, budget, or schedule of the project in any way if it were to take place.
Not a risk | The project manager has determined that the submitted risk cannot/will not affect the scope, budget, or schedule of the project in any form. If there scope, budget, or schedule is not affected, than the submitted risk is not actually a risk.
Tentatively place risk in RAID sheet | List the risk in the RAID sheet but do not give it a severity rating yet. Project manager will gather more information about the risk and its owner(s) before filling out RAID sheet
Set up meeting with person(s) who submitted risk | Talk to the person who originally submitted the risk to get more details about the risk. In this meeting, get the following information: issues leading to risk creation, probability of risk occuring, cost impact of risk, schedule impact of risk, and scope impact of risk.
Set up meeting with team lead who leads the project phase in which the risk was detected | Meeting with the appropriate team lead should include talking about the nature of the risk (schedule risk, budget risk, scope risk) and going over what strategies are being used to counteract the risk. Team lead should provide an updated probability of the risk occuring, risk's impact on the budget, and scope change percentage.
Associate risk with specific project task | Specify which task in the project schedule that the risk originates from and update RAID sheet with information
Does task have schedule slack to compensate for risk delaying delivery? | Project manager should determine whether or not the task that the risk is associated with is on the critical path according to the project schedule.
Set up meeting with affected team to brainstorm solutions | Get the team who is responsible for the at-risk task together and come up with mitigation plans that will resolve the risk before it becomes an issue.
Update RAID sheet with severity, mitigation, and contingency | Project manager will go back to RAID sheet and fill out remaining information that was not gathered the first time.
Initiate mitigation plan to prevent risk from turning into issue | Put the mitigation plan into affect immediately in order to prevent risk from happening. Inform affected people of this decision.
Monitor risk daily and receive updates from team where risk originated | Ensure that the risk is not turning into an issue by keeping an eye on how the at-risk task is developing. Team that risk is affecting should email project manager weekly with status updates regarding the risk until the risk has been fully mitigated.
Set up meeting with affected team to brainstorm solutions | Get the team who is responsible for the at-risk task together and come up with mitigation plans that will resolve the risk before it becomes an issue.
Update RAID sheet with severity, mitigation, and contingency | Project manager will go back to RAID sheet and fill out remaining information that was not gathered the first time.
Monitor risk weekly by getting updates from the team lead responsible for the at-risk task(s) | Ensure risk is being monitored and kept under controll by checking up with the team lead for which ever phase the at-risk task is in (i.e. development team lead if the at-risk task is related to the development of the project). A regular 30+ minute talk should be had where the team lead explains what he/she is doing to mitigate the risk.
Project manager should brainstorm mitigations/ contingencies for risk | Project manager should forumlate solutions to risk that will mitigate the risk without putting another task at risk.
Update RAID sheet with severity, mitigation, and contingency | Project manager will go back to RAID sheet and fill out remaining information that was not gathered the first time.
Monitor risk bi-weekly by getting updates from the team lead responsible for the at-risk task(s) | Ensure that the risk is being monitored and does not become a greater risk. Updates received from team lead should include a status of the at-risk task.
Would the risk make the task go over its predicted budget? | Project manager should look at the estimated budget in their project plan to determine if the at-risk task in going over that predicted amount.
Does the risk make the project go cash flow negative? | Project manager should look calculate the cost of other tasks happening concurrently to at-risk task as well as how much is expected to be paid for the delivery of the milestone to determine if the at-risk task sends the project to a negative cash flow.
Cut back on superfluous resources working on task | Assign all non-essential resources on at-risk task to other tasks that need to be worked on.
Update RAID sheet – add severity, mitigation, and contingency | Record risk on the RAID sheet and add its severity (high), mitigation plan, and contingency plan.
Monitor risk weekly and receive updates from team where risk originated | Make sure employee(s) working on at-risk task update project manager weekly about the budget of the task. Project manager should use these costs forecast the project budget and make adjustments to the project plan.
How much does the task go over its assigned budget? | Determine a numerical impact to the project budget that the risk would cause if it turned into an issue.
Update RAID sheet – add severity, mitigation, and contingency | Project manager will update the RAID sheet so that the risk has the appropriate severity associated with it (high) as well as a mitigation and contingency plan.
Cut back resources working on task by 50% | Take away 65% of the resources currently working on the assignment and allocate them to other tasks.
Monitor risk daily and receive updates from team where risk originated weekly | Project manager should check the risk daily to make sure task does not go over budget. The team working on the task should provide detailed breakdown of what part of the budget was spent to accomplish the task.
Update RAID sheet – add severity, mitigation, and contingency | Project manager will update the RAID sheet so that the risk has the appropriate severity associated with it (medium) as well as a mitigation and contingency plan.
Cut back resources working on task by 30% | Take away 30% of the resources currently working on the assignment and allocate them to other tasks.
Monitor risk weekly and receive updates from team where risk originated bi-weekly | Project manager should check risk weekly to ensure it does not turn into an issue. The team working on the task should provide detailed breakdown of what part of the budget was spent to accomplish the task.
Update RAID sheet – add severity, mitigation, and contingency | Project manager will update the RAID sheet so that the risk has the appropriate severity associated with it (low) as well as a mitigation and contingency plan.
Cut back resources working on task by 10% | Take away 10% of the resources currently working on the assignment and allocate them to other tasks.
Monitor risk monthly and receive updates from team where risk originated monthly | Project manager should check risk monthly to ensure that it is mitigated before moving on to new tasks. The team working on the task should provide detailed breakdown of what part of the budget was spent to accomplish the task.
Does the risk change the project/task scope? | With the information provided from both the person who submitted the risk and the team lead who has jurisdiction over the task in which the risk was spotted, decide if the risk changes any part of the project or task's scope.
Hold meeting with Requirements Engineer team lead | Discuss risk further with Requirements Engineer Lead to determine what impact on the project's/task's scope this risk has. In this meeting, determine how much of a change in scope percentage this risk poses.
How much work does this risk add to the task? | Project manager should determine what percentage of work the risk may add to the at-risk task based upon the information provided by the Requirements Engineer Lead.
Update RAID sheet – add severity, mitigation, and contingency | Project manager will update the RAID sheet so that the risk has the appropriate severity associated with it (high) as well as a mitigation and contingency plan.
Edit PMP to account for change in scope | Project manager will report change in scope on the PMP so that its permanently recorded and available for reference.
Allocate additional 25% of necessary resources to task | Ensure that the additional workload is met with additional resources to ensure task is completed on time.
Have working team email PM updates weekly to monitor the development of the risk | Make sure that team responsible for working on at-risk task keeps project manager up to date with developments with the task.
Update RAID sheet – add severity, mitigation, and contingency | Project manager will update the RAID sheet so that the risk has the appropriate severity associated with it (medium) as well as a mitigation and contingency plan.
Edit PMP to account for change in scope | Project manager will report change in scope on the PMP so that its permanently recorded and available for reference.
Have working team come in on weekends to make up for additional work | Have the working team come in on weekends until all additional work is completed so that resources are not taken away from other tasks.
Have working team email PM updates bi-weekly to monitor development of risk | Make sure that team responsible for working on at-risk task keeps project manager up to date with developments with the task.
Update RAID sheet – add severity, mitigation, and contingency | Project manager will update the RAID sheet so that the risk has the appropriate severity associated with it (low) as well as a mitigation and contingency plan
Edit PMP to account for change in scope | Project manager will report change in scope on the PMP so that its permanently recorded and available for reference.
Have working team spend 2 hours overtime on weekdays to account for additional work | Working team should spend additional hours working on at-risk task so that schedule is maintained and delivery of project is not delayed
Have working team email PM updates monthly to monitor development of risk | Make sure that team responsible for working on at-risk task keeps project manager up to date with developments with the task.
Continue to monitor and mitigate risks until they are resolved | All risks should be continued to monitored and actively mitigated in order to ensure that they do not turn into issues and affect the scope, budget, or schedule of the overall project.