## Sheet1
Group 08 - SE/CS/CE 4381 - Meeting Meetings
Date | Time | Attendees | Topics Discussed | Work Assigned | Due Date | Status
2020-01-17 | 5:00 - 5:43 PM | Mohammad Asif - present Dylan Capece - present Everett McCrea - present Luke Padgett - present Blake Stroud - present | • Discussed Project Assignment 1 requirements (SOW & PMP) • Decided which platform to draft the documents (Google Drive) • Decided what technology and business the SOW should consider • Divided work amongst members appropriately • Talked about when to hold next team meeting | Mohammad Asif - [Customer responsibilities] Dylan Capece - [Scale of work, scope of project] Everett McCrea - [acceptance criteria, project management plan] Luke Padgett - [components, out of scope] Blake Stroud - [Purpose of Document] | Jan 27 Jan 28 Jan 28 Jan 28 Jan 28 | Completed Completed Completed Completed Completed
2020-01-22 | 6:20 - 6:46 PM | Mohammad Asif - Present Dylan Capece - Present Everett McCrea - Present Luke Padgett - Present Blake Stroud - Present | • Discussed high-level implementation of the technology we are using for the SOW • Went over the various duties everyone is accountable for • Came to agreements on what specific parts of the technology needed to be included in the SOW • Answered questions pertaining to specific parts of the SOW | Mohammad Asif - [Customer responsibilities] Dylan Capece - [Scale of work, scope of project] Everett McCrea - [acceptance criteria, project management plan] Luke Padgett - [components, out of scope] Blake Stroud - [Purpose of Document] | Jan 27 Jan 28 Jan 28 Jan 28 Jan 28 | Completed Completed Completed Completed Completed
2020-01-29 | 6:20 - 6:40 PM | Mohammad Asif - Present Dylan Capece - Present Everett McCrea - Present Luke Padgett - Present Blake Stroud - Present | • Discussed Project Assignment 2 and its requirements • Divided work amongst team members • Discussed which software would be used to draft WBS • Started talking about overall structure of WBS and which tasks should be included | Mohammad Asif - [WBS diagram] Dylan Capece - [WBS diagram] Everett McCrea - [Business landscape / Business Value and PMP Presentation] Luke Padgett - [Business Requirements / Scope] Blake Stroud - [Business Requirements / Scope] | Feb 11 Feb 11 Feb 10 Feb 10 Feb 10 | Completed Completed Completed Completed Completed
2020-02-05 | 6:20 - 7:10 PM | Mohammad Asif - Present Dylan Capece - Present Everett McCrea - Present Luke Padgett - Present Blake Stroud - Present | • Worked on WBS and discussed which parts of the project needed to be included • Discussed the various requirements of the project that need to be brought up on the WBS • Decided on how the WBS should be structured (level headings and work packages) • Discuss design, development, testing, and deployment work packages that need be included on the WBS | Mohammad Asif - [WBS diagram] Dylan Capece - [WBS diagram] Everett McCrea - [WBS diagram] Luke Padgett - [WBS diagram] Blake Stroud - [WBS diagram] | Feb 11 Feb 11 Feb 11 Feb 11 Feb 11 | Completed Completed Completed Completed Completed
2020-02-12 | 6:22 - 6:32 PM | Mohammad Asif - Present Dylan Capece - Present Everett McCrea - Present Luke Padgett - Present Blake Stroud - Present | • Discussed project 3 requirements • Discussed how to download Microsoft Project • Assigned everyone workload that included learning Microsoft Project | Mohammad Asif - [Learn MS Project] Dylan Capece - [Learn MS Project] Everett McCrea - [Learn MS Project] Luke Padgett - [Learn MS Project] Blake Stroud - [Learn MS Project] | Feb 19 Feb 19 Feb 19 Feb 19 Feb 19 | Completed Completed Completed Completed Completed
2020-02-19 | 6:20 - 6:35 PM | Mohammad Asif - Present Dylan Capece - Present Everett McCrea - Absent Luke Padgett - Present Blake Stroud - Present | • Discussed project 3 requirements and progress so far • Reviewed Microsoft Project file • Decided who will be responsible for what portion of the remaining work and delegated work accordingly | Mohammad Asif - Meet Sunday at 3 to finish remaining work Blake Stroud - Meet Sunday at 3 to finish remaining work Everett McCrea - Meet Sunday at 3 to finish remaining work Dylan Capece - Meet Sunday at 3 to finish remaining work Luke Padgett - Review Microsoft Project File and SOW, see if costs are correct, meet Sunday at 3 if possible (scheduling conflict) | Feb 26 Feb 26 Feb 26 Feb 26 Feb 26 | Completed Completed Completed Completed Completed
2020-02-26 | 6:20 - 7:09 PM | Mohammad Asif - Present Dylan Capece - Present Everett McCrea - Present Luke Padgett - Present Blake Stroud - Present | • discussed risks with our project • Discussed issues that may occur in project • came up with mitigation plans/resolutions for risks and issues • came up with Actions for the RAID sheet • came up with decisions that would be implemented into project • reviewd RAID example to learn how to structure our project | Mohammad Asif - [come up with 2 risks, 2 actions, and 1 decision] Blake Stroud - [come up with 2 risks, 2 actions, and 1 decision] Everett McCrea - [come up with 2 risks, 2 actions, 2 issues, and 1 decision] Dylan Capece - [come up with 2 risks, 2 actions, and 1 decision] Luke Padgett - [come up with 2 risks, 2 actions, and 1 decision] | Mar 4 Mar 4 Mar 5 Mar 4 Mar 4 | Completed Completed Completed Completed Completed
2020-03-04 | 6:20 - 6:42 PM | Mohammad Asif - Present Dylan Capece - Present Everett McCrea - Present Luke Padgett - Absent Blake Stroud - Present | • Discussed revisions to MPP schedule • Discussed revisions to RAID document • Discussed schedule for RMP flowchart and RMP table • Assigned workload for RMP flowchart and RMP table • Worked on MPP modifications and tasks • Talked about how RMP flowchart and RMP table should be design | Mohammad Asif - [RMP Flowchart] Blake Stroud - [RMP Flowchart] Everett McCrea - [MPP revisions, RAID revisions] Dylan Capece - [RMP table] Luke Padgett - [RMP table] | Mar 8 Mar 8 Mar 6 Mar 10 Mar 10 | Completed Completed Completed Completed Completed
2020-03-09 | 5:30 - 5:45 PM | Mohammad Asif - Present Dylan Capece - Present Everett McCrea - Present Luke Padgett - Present Blake Stroud - Present | • Dicussed revisions made to RMP flowchart, RMP table, and MPP • Reviewed MPP schedule to make changes based on project 3 feedback • Divided revision and editing workload • Talked about changes in RAID document to account for 20% project progression • Discussed studying startegies for midterm test | Mohammad Asif - [Revise/edit RMP flowchart] Blake Stroud - [Revise/edit RMP table] Everett McCrea - [Revise/edit PMP presentation] Dylan Capece - [Revise/edit PMP document] Luke Padgett - [Revise/edit SOW and WBS] | Mar 10 Mar 10 Mar 10 Mar 10 Mar 10 | Completed Completed Completed Completed Completed
2020-03-30 | 5:15 - 5:32 PM | Mohammad Asif - Present Dylan Capece - Present Everett McCrea - Present Luke Padgett - Present Blake Stroud - Present | • Discussed Project 5 requirements • Viewed textbook's example for deliverables (governance plan, communication plan, stakeholder mapping) • Discussed who the stakeholders for the project would be • Discussed the communication plan documents and forms of delivering communication • Assigned work among group members • Discussed required changes needed to be made to RAID document | Mohammad Asif - [Communication plan, stakeholder mapping] Blake Stroud - [update RAID template, governance plan, Communication plan] Everett McCrea - [update RAID template, update PMP presentation & document, stakeholder mapping] Dylan Capece - [update RAID template, Communication plan, governance plan] Luke Padgett - [update RAID template, governance plan, stakeholder mapping] | Apr 6 Apr 6 Apr 6 Apr 6 Apr 6 | Completed Completed Completed Completed Completed
2020-04-06 | 5:15 - 5:24 PM | Mohammad Asif - Present Dylan Capece - Present Everett McCrea - Present Luke Padgett - Present Blake Stroud - Present | • Discussed remaining work for Project 5 • Briefly discussed project 6 requirements • Filled out Key Risks for Project 6 dashboard • Filled out Decisions for Project 6 dashboard | Mohammad Asif - [Review deliverables] Blake Stroud - [Review deliverables] Everett McCrea - [Review deliverables] Dylan Capece - [Review deliverables] Luke Padgett - [Review deliverables] | Apr 9 Apr 9 Apr 9 Apr 9 Apr 9 | Completed Completed Completed Completed Completed
2020-04-13 | 5:15 - 6:04 PM | Mohammad Asif - Present Dylan Capece - Present Everett McCrea - Present Luke Padgett - Present Blake Stroud - Present | • Discussed project deliverabels for project 6 • Referenced prior documents to help in filling out project dashboard • Assigned remaining work among team • As a group, updated MPP to reflect 40% completion • Worked on RAID risks based on updated MPP | Mohammad Asif - [update MPP, update RAID, dashboard: planned activities, key risks, key actions] Blake Stroud - [update MPP, update RAID, dashboard: key achievements, key milestones, key risks] Everett McCrea - [update MPP, update RAID, dashboard: summary, status, financials, key risks, decisions] Dylan Capece - [update MPP, update RAID, dashboard: timeline, key risks, issues/risks, key actions] Luke Padgett - [update MPP, update RAID, dashboard: major milestones, key milestones, key risks, decisions] | Apr 15 Apr 15 Apr 15 Apr 15 Apr 15 | In progress In progress In progress In progress In progress