## Risks
High Risk
Med Risk | Project - Issues and Risks | [6 empty] | DashBoard?
Low Risk | Item # | Issue/Risk | Description | Resolution Plan / Mitigation Plan | Contingency Plan | Due Date | Owner
| R-1 | Risk | Development of server/back-end service tier applications may be delivered late and cause delivery of back-end development to delay due to lack of experienced developers | 1) Have development engineer 3 work weekends to catch up to schedule 2) Contract service tier applications workload to 3rd party developer that are experienced with using SQL | 1) Dedicate all available testing team employees to catch up task on time 2) Hire 2 additional development engineers and assign them to at-risk tasks | 2020-07-16 | Development Engineer 3 | Y
| R-2 | Risk | Development of host computer system network between mobile application and RF sensors may be delivered late and cause finalization of host computer system to run late due to a lack of communication between the Design Engineer Lead and Development Engineer Lead | 1) Establish meeting time for design engineer lead and development engineer lead to meet up 2) Have Design Engineer Lead and Development Engineer Lead exchange contact information so that they may contact each other regularly | 1) Directly set up meeting with PM involved to establish a channel of communication | 2020-04-09 | Design Engineer Lead | Y
| R-3 | Risk | Regression testing may not finish on time, causing end-to-end testing to start late due to test engineer 1 & 2 being absent from work | 1) Have testing engineer lead dedicate extra hour of work each weekday until work is caught up 2) Allow test engineers 1 & 2 to work on regression testing out of office | 1) Have testing team lead work weekends until task is caught up 2) Pull additional test engineer from internal resources to help test engineers 1 & 2 | 2020-07-20 | Testing Engineer Lead | Y
| R-4 | Risk | Integration testing of DBMS into server/back-end system has not yet been completed which may result in delay to finalization document of the server/back-end development because test engineer 3 was absent for two days | 1) Assign Testing Engineer lead to aid in workload 2) Start the server/back-end finalization document early and only fill out information that has been complete so that it is not started late. 3) Pull internal resources from other company projects to help with the task | 1) Have both testing engineer lead and testing engineer 3 work weekends until task is caught up 2) Expedite testing process by removing 20% of test cases | 2020-08-25 | Testing Engineer 3 | N
| R-5 | Risk | Building of server/back-end schema has not been completed which may result in a delay to the finalization document of the server/back-end development because development engineer 3 was not trained well enough to handle workload | 1) Have Development Engineer Lead help in workload 2) Provide training for Development Engineer 3 to ensure he is adequately prepared for workload 3) Have Design Engineer 2 help with schema development as he has prior experience with it | 1) Have all available employees on development team switch to task until it is completed 2) Contract building of server/back-end schema to 3rd party contractor | 2020-07-12 | Development Engineer 3 | Y
| R-6 | Risk | Testing of mobile application UI/UX not yet complete, may cause delay in finalizing UI/UX testing due to testing engineer 12 not getting enough work done during work duration | 1) Have testing engineer 12 work extra hours on weekday until caught up 2) Have project manager observe Test Engineer 12's during working hours so that he is pressured to perform better | 1) Have testing engineer 12 and testing engineer 11 work weekends until work is caught up 2) Hold performance meeting with test Engineer 12 and tell him how to improve his work pace. Have him work overtime until task is completed | 2020-07-10 | Testing Engineer 12 | Y
| R-7 | Risk | Finalization of server/back-end development may be late and cause testing of server/back-end to start late due to development engineer 2 running late on his assigned tasks | 1) Have development engineer 2 work weekends to catch up to schedule 2) Allow testing to start early with whatever codebase is already developed as to not start late | 1) Have development engineer 2 and development engineer lead work weekends until work is caught up | 2020-08-13 | Development Engineer 3 | N
| R-8 | Risk | Finalization document of web page testing may not finish on time due to conflicts between Test Engineers 8 & 9. This may cause a delay in defect testing initiation | 1) Have testing engineer 2 help in workload 2) Schedule meeting involving test engineers 8 & 9 in order to come to a compromise over the conflicting topic | 1) Assign all available testing engineers to task until it is complete 2) If conflict not yet resolved, give authority of the conflict resolution to Test Engineer 8 | 2020-06-15 | Testing Engineer 12 | N
| R-9 | Risk | Finalized UI/UX testing not complete on time, could cause delay in defect fixing start date due to testing engineer 12 having a delayed start time | 1) Have testing engineer 12 work extra hours in order to compensate for late start 2) Assign part of the workload to test engineer 4 3) Get resources from other projects within the company to help on the at-risk task | 1) Assign all available testing engineers to task until it is complete | 2020-07-15 | Testing Engineer 12 | N
| R-10 | Risk | Persistent conflict between Project Manager and Development Engineer Lead may be cause a delay in the finalization of of development phase document (milestone 03). This may delay the deployment team from connecting system components | 1) Seek conflict arbitration from internal upper management on the at-conflict topic 2) Have deployment team begin connection of system with whichever subsystems are already completed 3) Schedule team building exercises so that Project Manager and Development Team Lead are able to better cooperate with one another | 1) Have development Engineer Lead be moved to new project within company and assign new Development Engineer Lead to Development Engineer 3 2) Hire new project manager to take over project for the remaining duration | 2020-09-10 | Project Manager | N

## Issues
High Risk
Med Risk | Project - Issues
Low Risk | Item # | Issue/Risk | Description | Impact | Resolution Plan / Mitigation Plan | Due Date | Owner
| I-01 | Issue | Testing of the host computer system's data encryption is over budget by 54% of planned cost due to prolonged development. This has made the testing phase cash flow negative | Overall profit margin of the project will be reduced due to over expenditure | Reduce the number of resources working on defect testing, regression testing, and end-to-end testing while maintaining their current schedules | 2020-07-29 | Project Manager
| I-02 | Issue | Testing of real-time parking lot update for the host computer system has not been completed on time, causing the finalization of the host computer testing to run late | Host computer system will not have finished testing in time for defect testing, causing defect testing to start later than its late start | Have testing engineer lead come in during weekend to finish up testing so that finalization of host computer system testing is delayed as short as possible | 2020-08-04 | Testing Engineer Lead

## Actions
Project Action List
# | Description | Originator | Owner | Date Assigned | Date Needed | Date Closed | Comments | Status
1 | Design Engineers 1 - 5 will monitor development team to ensure their implementation is correct with design blueprints | Design Engineer Lead | Development Engineer Lead | 2020-04-12 | 2020-05-08 |  | Design engineers should only check in with development engineers once a day | IN PROGRESS
2 | Testing Engineer Lead will meet with Development Team Lead regularly to discuss issues regarding development process over lunch | Testing Engineer Lead | Development Engineer Lead | 2020-04-29 | 2020-09-24 |  |  | IN PROGRESS
3 | Requirements Engineer Lead will inspect codebase provided by development team weekly to ensure the non-functional requirements are being met | Requirements Engineer Lead | Development Engineer Lead | 2020-05-29 | 2020-04-09 |  | Ensure that requirements are being properly implemented during development | IN PROGRESS
4 | Development Engineer Lead will provide weekly write-ups to PM regarding development of project | PM | Development Engineer Lead | 2020-04-09 |  |  | Allow PM to modify schedule based on the input provided in Development Manager Lead's reports | IN PROGRESS
5 | Diagrams of server/back-end schema shall be sent to UTD database administrator weekly to ensure they are compatible with current UTD database | Development Engineer Lead | UTD Database Administrator | 2020-05-02 | 2020-06-10 |  | Ensure that development team is designing the server/back-end schema correctly the first time around to avoid revision | IN PROGRESS
6 | Conduct stakeholder meeting to discuss non-functional requirements at least once a month | PM | PM | 2020-03-17 |  |  | Stakeholders should email PM if they will be able to attend | IN PROGRESS
7 | Design Engineer Lead and Deployment Engineer Lead shall meet once a month to review how connection of system should work at deployment time | Design Engineer Lead | Deployment Engineer Lead | 2020-06-20 | 2020-11-09 |  |  | IN PROGRESS
8 | Requirements team will hold daily meetings in the morning to discuss progression of interview questions | Requirements Engineer Lead | Requirements Engineer Lead | 2020-02-19 |  | 2020-02-27 |  | CLOSED
9 | Requirements Team Lead will monitor design team to ensure requirements are captured properly in design blueprints | Requirements Engineer Lead | Design Engineer Lead | 2020-04-02 |  | 2020-05-08 |  | CLOSED
10 | Contact development engineer lead each week to check in on progress | PM | PM | 2020-04-09 |  |  | Check-ins will be held each Thursday at 4:00 pm | IN PROGRESS

## Decisions
Project Decision List
# | Description | Owner | Date | Comments | Status
D-1 | Development of the mobile application shall be built using Java 8 | Development Engineering Lead | 2020-02-28 | Java 8 is the language most capable for accomplishing building the mobile application and will allow the development team to utilize preexisting frameworks to help in the development of the mobile application Attendees: Requirements Engineer Lead, Development Engineer Lead, Testing Engineer Lead, Design Engineer Lead | CLOSED
D-2 | Host computer system will use the Ubuntu OS version 19.10 | Development Engineer Lead | 2020-02-20 | OS was chosen for its secure architecture and lack of preinstalled software packages. Attendees: Development Engineer Lead | CLOSED
D-3 | Testing environment shall be built using Junit version 4.13 | Testing Engineer Lead | 2020-04-13 | Most test engineers know how to use Junit from previous work experience. Attendees: Test Engineer Lead, Test Engineers 1 - 12 | CLOSED
D-4 | The developed database shall be built using SQL version 14.0 | Design Engineer Lead | 2020-02-21 | Most employees working on the project know SQL better than any other relation database language, allowing us to save time on development of the server/back-end Attendees: Project Manager, Design Engineer Lead, Requirements Engineer Lead, Development Engineer Lead, Testing Engineer Lead | CLOSED
D-5 | UTD's database administrator will need to be present during the customer interviews to provide information regarding the design of the UTD schema | Requirements Engineering Lead | 2020-02-20 | Understanding the schema design of UTD's database is very important to know during early phase of project so that the mobile application services are not design incorrectly Attendees: Requirements Engineering Lead, customer | CLOSED