## Risks
High Risk |  |  |  | Mohammad Asif, Dylan Capece, Blake Stroud, Luke Padgett, Everett McCrea
Med Risk | Project - Issues and Risks | [6 empty] | DashBoard?
Low Risk | Item # | Issue/Risk | Description | Resolution Plan / Mitigation Plan | Contingency Plan | Due Date | Owner
| R-12 | Risk | Persistent conflict between Project Manager and Development Engineer Lead may be cause a delay in the finalization of of development phase document (milestone 03). This may delay the deployment team from connecting system components | 1) Seek conflict arbitration from internal upper management on the at-conflict topic 2) Have deployment team begin connection of system with whichever subsystems are already completed 3) Schedule team building exercises so that Project Manager and Development Team Lead are able to better cooperate with one another | 1) Have development Engineer Lead be moved to new project within company and assign new Development Engineer Lead to Development Engineer 3 2) Hire new project manager to take over project for the remaining duration | 2020-09-10 | Project Manager | N
| R-13 | Risk | Defect testing may finish late by 4 days due to test engineer 3 not starting prerequisite task of finalizing server/back-end testing on time. This may cause the drafting of the final testing document to run late. | 1) Have Testing Engineers 1 & 4 help with finalizing the server/back-end document 2) Assign additional employees to defect testing (testing engineers 5, 10, and 11) to expedite the work and shorten the schedule | 1) Assign Testing Engineer Lead to both the prerequisite task (finalizing server/back-end testing) and defect testing to help with workload 2) Have Testing Engineer 1, 4, 6, 8, and 9 work overtime on defect testing to ensure it completes on time | 2020-09-18 | Testing Engineer 3 | Y
| R-14 | Risk | Launch of database may be late by 6 days due to testing engineer 3 having not started prerequisite task of finalizing server/back-end testing on time. This may delay the connection of systems components. | 1) Have Testing Engineer 3 work overtime to complete prerequisite task so that the launch of database can occur on schedule 2) Assign Testing Engineer Lead to help with the finalization of server/back-end testing | 1) Have Deployment engineer 3 work overtime to launch database as soon as possible 2) Have Deployment Engineer 1 work with Deployment Engineer 3 to expedite work | 2020-09-09 | Testing Engineer 3 | Y
| R-15 | Risk | Establishment of connection between UTD database and app database may be late by 6 days due to testing engineer 3 having not started prerequisite task of finalizing server/back-end testing on time. This may delay the connection of system components. | 1) Have Testing Engineer 3 work weekends in order to catch up on work so that the connection between UTD database and app database does not start late 2) Assign Testing Engineer Lead to help with the finalization of server/back-end testing | 1) Have Deployment engineer 1 work overtime to connect the UTD database and app databases on time 2) Contact UTD database administrator to ask for administrator permissions so that task can move forward quicker without cooperation of customer required. | 2020-09-07 | Testing engineer 3 | N
| R-16 | Risk | Drafting of final testing document may run over budget by 14% due to Testing Engineer Lead demanding larger salary. This may cause the testing phase to go cash flow negative as well as make the review and finalization of the testing document (milestone 04) run over budget. | 1) Delay salary negoiations with Testing Engineer Lead until testing phase has concluded 2) Talk with internal upper management about alternatives to salary increase (benefits, payment via stocks, etc.) | 1) Deny Testing Engineer Lead salary increase 2) Take Testing Engineer Lead off project and give workload to Testing Engineer 12 instead 3) Meet with customer stakeholders to discuss increase in project budget 4) Submit proposal for price increase to customer | 2020-09-25 | PM | N
| R-17 | Risk | Capturing of car information from parking lot gates may be late due to Deployment Engineer 4 unexpectedly terminating employment. This may cause the connection of system components to run late due to lack of employee resources. | 1) Begin searching for permanent replacement employee to take on responsibilities of Deployment Engineer 4 2) Give workload to Deployment Engineer 1 3) Contract temporary worker to fill in for Deployment Engineer 4 | 1) Request for additional employee working on another project within the company 2) Have Deployment Engineer 1 work weekends and overtime to catch up on the work left behind by Deployment Engineer 4 | 2020-09-28 | PM | Y
| R-18 | Risk | Connection of system components may be delivered late by up to 14 days due to Deployment Engineer 4 unexpectedly terminating employment. This may cause a delay in training the clients on the system. | 1) Begin searching for replacement employee 2) Give workload to Deployment Engineer 2 3) Have Deployment Engineer Lead work weekends on his tasks as well as tasks left behind by Deployment Engineer 4 | 1) Begin connection of system components immediately with subcomponents that have already been delivered so that work can begin earlier than expected 2) Request for additional employee working on another project within the company | 2020-10-20 | PM | Y
| R-19 | Risk | Review of testing document (milestone 04) may be late by 5 days due to Testing Engineer Lead expected absence for other business matters during that week. This may delay the finalization of the testing document. | 1) Assign Testing Engineer 12 to review work on behalf of the Testing Engineer Lead 2) Allow Testing Engineer Lead to review document while out of office during his freetime | 1) Have Testing Engineers 12, 1, and 7 work overtime to finish reviewing the final testing document 2) Assign additional employees (Testing Engineer 1 & 2) to assignment to ensure timely delivery | 2020-09-24 | Testing Engineer Lead | N
| R-20 | Risk | Training clients on system may be delayed by up to 14 days due to Deployment Engineer 4 unexpectedly terminating employment. This may cause the drafting of the final deployment document to be late. | 1) Begin searching for replacement employee 2) Borrow Deployment Engineer from other project within company to work on task | 1) Have Development Engineer Lead be a stand-in for Deployment Engineer 4 as he is aware of system functionalities and could adequately train the client on how to use the system | 2020-11-10 | Deployment Engineer Lead | N
| R-21 | Risk | Launch of database may be late due by 2 days to Deployment Engineer 3 being new to the project and inexperienced with workload. This may cause the connection of the system components to be late. | 1) Assign Deployment Engineer Lead to watch over Deployment Engineer 3 during launch of database 2) Begin connection of system components early with whichever components have already been delivered as to not start late on the task | 1) Have both Deployment Engineer 3 and Deployment Engineer Lead work overtime to ensure Launch of database does not get delayed further | 2020-09-09 | Deployment Engineer 3 | N
| R-22 | Risk | Release of the mobile application on to the Apple App Store may be late due to unexpectedly long waiting time for a response back from Apple representative. This may cause the training of the clients to start and end late. | 1) Have Deployment Engineer 3 call Apple weekly to get a response 2) Set up video meeting between Deployment Engineer 3, PM, and an Apple representative to move along the process of publishing project's mobile application to the Apple App Store | 1) Have internal upper management attempt to get a hold of Apple representative using their connections at the company 2) Send formal letter to Apple with request of publishing an App on their Apple App Store | 2020-10-21 | Deployment Engineer 3 | Y
Project - Risks -- CLOSED
| Item # | Issue/Risk | Description | Close Reason | Date Closed | Closed By
| R-1 | Risk | Development of server/back-end service tier applications may be delivered late and cause delivery of back-end development to delay due to lack of experienced developers | Training provided to developers on time allowing them to better hand their workload and complete tasks on time | 2020-07-16 | Development Engineer 3
| R-2 | Risk | Development of host computer system network between mobile application and RF sensors may be delivered late and cause finalization of host computer system to run late due to a lack of communication between the Design Engineer Lead and Development Engineer Lead | Communication channel established between Design Engineer Lead and Development Engineer Lead in the form of weekly email chains | 2020-04-11 | Design Engineer Lead
| R-3 | Risk | Regression testing may not finish on time causing end-to-end testing to start late due to test engineer 1 & 2 being absent from work | Testing Engineer 1 completed work from home while Testing Engineer 2's work was given to Testing Engineer 11 | 2020-07-20 | Testing Engineer Lead
| R-4 | Risk | Integration testing of DBMS into server/back-end system has not yet been completed which may result in delay to finalization document of the server/back-end development because test engineer 3 was absent for two days | Testing Engineer 3 worked overtime and weekends until work load was caught up and delivered tasks on time | 2020-08-26 | Testing Engineer 3
| R-5 | Risk | Building of server/back-end schema has not been completed which may result in a delay to the finalization document of the server/back-end development because development engineer 3 was not trained well enough to handle workload | Workload was given to Development Engineer 5 instead and Development Engineer 3 is undergoing training | 2020-07-12 | Development Engineer 3
| R-6 | Risk | Testing of mobile application UI/UX not yet complete, may cause delay in finalizing UI/UX testing due to testing engineer 12 not getting enough work done during work duration | PM monitored work ethic of Testing Engineer 12 to ensure that necessary pressure was applied so that the task could be completed on time | 2020-07-02 | PM
| R-7 | Risk | Finalization of server/back-end development may be late and cause testing of server/back-end to start late due to development engineer 2 running late on his assigned tasks | Development Engineer Lead stepped in to help in workload during his breaks as well as after normal working hours | 2020-08-10 | Development Engineer Lead
| R-8 | Risk | Finalization document of web page testing may not finish on time due to conflicts between Test Engineers 8 & 9. This may cause a delay in defect testing initiation | Mediation between Testing Engineers 8 & 9 conducted by Testing Engineer Lead and a suitable compromise was made to ensure conflict is resolved for now | 2020-06-10 | Testing Engineer Lead
| R-9 | Risk | Finalized UI/UX testing not complete on time, could cause delay in defect fixing start date due to testing engineer 12 having a delayed start time | Testing Engineer 12 worked overtime during weekdays on request of PM in order to ensure timely delivery | 2020-07-20 | PM
| R-10 | Risk | Finalized web interface requirements questions not delivered on time, may cause delay in finalization of project requirements document due to requirements engineer 3 being absent from work | Requirements Engineer 3 agreed to work from out-of-office and was able to submit requirements questions on time. | 2020-04-07 | Requirements Engineer 3
| R-11 | Risk | Finalized UI/UX requirements questions not yet completed due to requirements engineer 5 being absent from work. This may cause the finalized requirements doucment (milestone 01) to be delivered late. | Workload was given to Requirements Engineer Lead instead and workload was delivered on time | 2020-04-10 | Requirements Engineer Lead

## Actions
Project Action List
# | Description | Originator | Owner | Date Assigned | Date Needed | Date Closed | Comments | Status
1 | Design Engineers 1 - 5 will monitor development team to ensure their implementation is correct with design blueprints | Design Engineer Lead | Development Engineer Lead | 2020-04-12 | 2020-05-08 |  | Design engineers should only check in with development engineers once a day | IN PROGRESS
2 | Testing Engineer Lead will meet with Development Team Lead regularly to discuss issues regarding development process over lunch | Testing Engineer Lead | Development Engineer Lead | 2020-04-29 | 2020-09-24 |  |  | IN PROGRESS
3 | Requirements Engineer Lead will inspect codebase provided by development team weekly to ensure the non-functional requirements are being met | Requirements Engineer Lead | Development Engineer Lead | 2020-05-29 | 2020-04-09 |  | Ensure that requirements are being properly implemented during development | IN PROGRESS
4 | Development Engineer Lead will provide weekly write-ups to PM regarding development of project | PM | Development Engineer Lead | 2020-04-09 |  |  | Allow PM to modify schedule based on the input provided in Development Manager Lead's reports | IN PROGRESS
5 | Diagrams of server/back-end schema shall be sent to UTD database administrator weekly to ensure they are compatible with current UTD database | Development Engineer Lead | UTD Database Administrator | 2020-05-02 | 2020-06-10 | 2020-06-12 | Ensure that development team is designing the server/back-end schema correctly the first time around to avoid revision | CLOSED
6 | Conduct stakeholder meeting to discuss non-functional requirements at least once a month | PM | PM | 2020-03-17 |  |  | Stakeholders should email PM if they will be able to attend | IN PROGRESS
7 | Design Engineer Lead and Deployment Engineer Lead shall meet once a month to review how connection of system should work at deployment time | Design Engineer Lead | Deployment Engineer Lead | 2020-06-20 | 2020-11-09 |  |  | IN PROGRESS
8 | Requirements team will hold mock interviews before meeting with customer to ensure questions are worded clearly | Requirements Engineer Lead | Requirements Engineer Lead | 2020-02-19 | 2020-02-27 | 2020-02-27 |  | CLOSED
9 | Requirements Team Lead will monitor design team to ensure requirements are captured properly in design blueprints | Requirements Engineer Lead | Design Engineer Lead | 2020-04-02 |  | 2020-05-08 |  | CLOSED
10 | Contact development engineer lead each week to check in on progress | PM | PM | 2020-04-09 |  |  | Check-ins will be held each Thursday at 4:00 pm | IN PROGRESS
11 | Testing Engineer Lead has decided to sit-in on some of the workload conducted by Testing Engineer 3 and provide training for tasks that she does not have much experience with | Testing Engineer 3 | Testing Engineer Lead | 2020-08-08 | 2020-08-08 | 2020-09-04 | Testing Engineer Lead shall lightly monitor Testing Engineer 3 by moving his office space to hers and help with any work that she may have trouble with | CLOSED
12 | A new Deployment Engineer shall be brought in from another project within the company as a fill-in until a suitable replacement has been found | Deployment Engineer Lead | PM | 2029-08-08 | 2020-09-09 | 2020-08-10 | New Deployment Engineer shall attend meeting with PM and Deployment Engineer Lead to get caught up on the project objective and progress | CLOSED
13 | Deployment Engineer Lead shall contact UTD upper management in order to get a location on where the host computer system shall be installed at | Deployment Engineer Lead | Deployment Engineer Lead | 2020-07-09 | 2020-07-16 | 2020-07-22 | Deployment engineer Lead should ensure that target location for the installation of the host computer system on the UTD campus is still the desired location before installation begins | CLOSED
14 | Deployment Engineer Lead shall keep UTD database administrator up-to-date about the launch of the database when it is time for database to be deployed | Deployment Engineer Lead | UTD Database Administrator | 2020-09-02 | 2020-09-09 |  | Deployment Engineer Lead will let UTD database administrator know any complications in the launch of the database and shall let him/her know when the database is ready to be turned on | IN PROGRESS

## Decisions
Project Decision List
# | Description | Owner | Date | Comments | Status
D-1 | Host computer system will use the Ubuntu OS version 19.10 | Development Engineer Lead | 2020-02-20 | OS was chosen for its secure architecture and lack of preinstalled software packages. Attendees: Development Engineer Lead | CLOSED
D-2 | UTD's database administrator will need to be present during the customer interviews to provide information regarding the design of the UTD schema | Requirements Engineering Lead | 2020-02-20 | Understanding the schema design of UTD's database is very important to know during early phase of project so that the mobile application services are not design incorrectly Attendees: Requirements Engineering Lead, customer | CLOSED
D-3 | The developed database shall be built using SQL version 14.0 | Design Engineer Lead | 2020-02-21 | Most employees working on the project know SQL better than any other relation database language, allowing us to save time on development of the server/back-end Attendees: Project Manager, Design Engineer Lead, Requirements Engineer Lead, Development Engineer Lead, Testing Engineer Lead | CLOSED
D-4 | Development of the mobile application shall be built using Java 8 | Development Engineering Lead | 2020-02-28 | Java 8 is the language most capable for accomplishing building the mobile application and will allow the development team to utilize preexisting frameworks to help in the development of the mobile application Attendees: Requirements Engineer Lead, Development Engineer Lead, Testing Engineer Lead, Design Engineer Lead | CLOSED
D-5 | Meetings between customer and team members shall take place via Skype instead of face-to-face | PM | 2020-04-01 | In order to prevent spread of disease, Skype meetings shall be conducted in place of face-to-face meetings. Meeting times and topics shall remain the same. Attendees: UTD Upper management, PM | OPEN
D-6 | Testing environment shall be built using Junit version 4.13 | Testing Engineer Lead | 2020-04-13 | Most test engineers know how to use Junit from previous work experience. Attendees: Test Engineer Lead, Test Engineers 1 - 12 | CLOSED
D-7 | UTD database administrator and UTD network administrator shall be present when deployment team is connecting system together. | UTD database administrator | 2020-09-01 | UTD database administrator and UTD network administrator should develop better understanding of various subsystems of the project before it goes live. Attendees: Deployment Engineer Lead, UTD database administrator, UTD network administrator | OPEN
D-8 | Testing Engineer 12 will act as a stand-in for the Testing Engineer Lead during the Drafting, Review, and Finalization of the testing phase document. | Testing Engineer 3 | 2020-09-03 | Testing Enginer Lead has other business matters to conduct during week when the testing phase is coming to a close. In order to ensure that the testing phase does not delay, Testing Engineer 12 shall be given the go-ahead to perform the duties of Testing Engineer Lead during his absence. Attendees: PM, Testing Engineer 12, Testing Engineer Lead | OPEN

## Issues
High Risk
Med Risk | Project - Issues
Low Risk | Item # | Issue/Risk | Description | Impact | Resolution Plan / Mitigation Plan | Due Date | Owner
| I-05 | Issue | Review of the development document (milestone 03) is one week late on delivery due to Development Engineer Lead unexpectedly contracting the flu. This has caused the finalization of the development document (milestone 03) to go past deadline by 3 days. | Development phase will be concluded late - resulting in late delivery of project milestone | 1) Have Development Engineer Lead work overtime and weekends once he comes back to office 2) Give workload to development Engineer 4 and have him sign off on milestone 03 3) Send review documentation and finalization documentation to Development Engineer Lead while in the hospital to work on | 2020-09-10 | Development Engineer Lead
| I-06 | Issue | Testing of service tier applications not finished on time due to testing equipment/supplies arriving later than expected. This has caused the finalization of server/back-end document to become late. | Finalization of the server/back-end testing will start late | 1) Having testing engineer 3 work overtime to compensate for late delivery of supplies 2) Have testing engineers 1 & 2 help with workload including the finalization of the server/back-end doucment | 2020-09-06 | Testing Engineer 3
| I-07 | Issue | Finalization of development document (milestone 03) has not yet been started and has passed deadline by 3 days due to prerequisite task not being completed on time. This will cause milestone 03 to be delivered late and payment for the milestone will not be received on the expected date.This will also cause defect testing to start late. | Development phase will be concluded late and project milestone delivered late. Defect testing will begin late | 1) Have all available development engineers work towards completing prerequisite task to enable this task to start as early as possible 2) Have all available development engineers work on this task as soon as prerequisite task has been completed 3) Hold meeting with customer to request for rescheduled delivery of milestone 03 4) Have all available development engineers work overtime to ensure this task is completed as soon as possible | 2020-09-07 | PM
| I-08 | Issue | Finalization of server/back-end testing has not yet been started and is already past deadline due to the prerequisite task of conducting service tier applications not being completed on time. This will cause a a delay in the start date of the following tasks: defect testing (155), launch database (164), and establish connection between UTD database and app database (165). | Defect testing, lauching database, and establishing connection between UTD & mobile app database will start late | 1) Assign Testing Engineer 1 & 7 in addition to testing Engineer 3 and have all of them work overtime and weekends until task is completed 2) Contact customer to request an extentsion to the project tasks 3) Begin defect testing before the finalized server/back-end testing is finsihed to ensure it does not end late 4) Attempt to launch database as it is right now and work on testing it later in the project 5) establish a connection between UTD database and mobile app database and have testing going on in background | 2020-09-07 | Testing Engineer 3
Project - Issues -- CLOSED
| Item # | Issue/Risk | Description | Close Reason | Date Closed | Closed By
| I-01 | Issue | Customer interviews not conducted on time due to requirements questions being incomplete. Interviews will be rescheduled to later date which will delay drafting of final requirement document | Interviews were conducted digitally one week after the expected date and requirements team memebers were all present | 2020-05-05 | Requirements Engineer Lead
| I-02 | Issue | Finalized requirements document (milestone 01) not delivered on time due to absence of requirements engineer team memebrs. This is causing design phase to start late | Overtime was enforced on the requirements team members that were present and task was completed 4 days after the expected deadline | 2020-04-07 | Requirements Engineer Lead
| I-03 | Issue | Testing of the host computer system's data encryption is over budget by 54% of planned cost due to prolonged development. This has made the testing phase cash flow negative | Budget impact will come out of the profit margin for project. Internal upper management informed about the impact and agreed to decision | 2020-07-27 | Project Manager
| I-04 | Issue | Testing of real-time parking lot update for the host computer system has not been completed on time, causing the finalization of the host computer testing to run late | Testing Engineer 5 worked the following weekend in order to get task delivered by start of the next week. | 2020-07-05 | Testing Engineer 5